# Goal

Increase the number of students scoring 95+ in Grade 10 Math within 30 days using:

- Design Thinking (student-centered)

- AI (for diagnosis, personalization, feedback and efficiency)

# 🔹 DESIGN THINKING PROCESS

## 1️⃣   EMPATHISE — Understand Your Students Deeply (Days 1–3)

Objective: Identify why students are stuck at 85–94 and what is blocking 95+.

### Actions

| Stakeholder | Method | AI Use |
| --- | --- | --- |
| Students | Short Google Form + reflection | AI summarises patterns |
| Students | Analyse last 3 papers | AI error categorisation |
| Teacher | Time-on-topic & weak areas | AI heatmap |

### Key Questions

- Which chapters cost them the most marks?

- Are errors conceptual, careless, speed-based, or presentation-based?

- Are they losing marks in HOTS, case studies, or basic steps?

### AI Tools

- ChatGPT / Claude → Error pattern analysis

- Google Forms + Sheets → Data collection

- Excel/AI → Cluster students by weakness

## 2️⃣     DEFINE — Clearly State the Problem (Day 4)

Convert insights into a sharp problem statement.

### Example:

“Most students scoring 85–94 lose marks due to
(a) careless algebraic slips,
(b) incomplete steps in proofs, and
(c) poor handling of case-based questions — not due to lack of concept.”

This becomes your design challenge:

“How might we help students reduce avoidable errors and improve answer quality within 30 days?”

## 3️⃣    IDEATE — Generate Targeted Solutions (Days 5–6)

Brainstorm strategies for each type of problem.

Problem Type; Solution; AI Use. Careless mistakes; Daily 10-min accuracy drills; Auto-generated. Weak proofs; Step-frame templates; AI-generated. Case study; Pattern-based practice; AI curated. Slow students; Timed micro-tests; AI timers + feedback. Presentation; Model answers; AI formatting.

## 4️⃣   PROTOTYPE — Create Small, Fast Interventions (Days 7–10)

Create low-effort, high-impact prototypes:

### Prototypes

- Daily 15-min AI worksheet personalised per student.

- Proof skeletons where students fill steps.

- Error log book (students maintain mistake diary).

- 3-level tests (Easy → Moderate → Board-like).

- Peer teaching for top students.

### AI role

- Generate variant questions daily

- Auto-check MCQs

- Create hint-based feedback

## 5️⃣   VALIDATE — Test What Works (Days 11–15)

### Measure:

- Error reduction rate

- Speed improvement

- Step completeness

- Marks improvement in weekly tests

### Decision:

Keep only what improves performance by ≥10%.

## 6️⃣   IMPLEMENT — Full-Scale Rollout (Days 16–30)

### Structure

| Daily | Weekly |
| --- | --- |
| 15 min accuracy drill | Full mock test |
| 20 min targeted practice | Error review |
| 10 min reflection | Remedial grouping |

Students are grouped dynamically:

- Group A (95+) → HOTS, Olympiad-style

- Group B (90–94) → Precision + presentation

- Group C (85–89) → Concept strengthening

AI reshuffles groups weekly.

🔷 FLOWCHART

┌──────────────┐

│     Scope    │

│ Improve 95+  │

└──────┬───────┘

│

┌──────▼───────┐

│   Empathise  │

│ Student data │

│ Error types  │

└──────┬───────┘

│

┌──────▼───────┐

│    Define    │

│ Core problem │

└──────┬───────┘

│

┌──────▼───────┐

│    Ideate    │

│ Target fixes │

└──────┬───────┘

│

┌──────▼───────┐

│  Prototype   │

│ Micro tools  │

└──────┬───────┘

│

┌──────▼───────┐

│   Validate   │

│ Test impact  │

└──────┬───────┘

│

┌──────▼───────┐

│  Implement   │

│ Scale & track│

└──────────────┘

# 🧠 Why This Works

| Traditional | Design Thinking + AI |
| --- | --- |
| More practice | Smarter practice |
| Same for all | Personalized |
| Syllabus driven | Error driven |
| Teacher intuition | Data + insight |
| Static groups | Dynamic grouping |

# 🌟 Expected Outcome

- 30–50% reduction in careless errors

- 15–25% improvement in case study questions

- 10–15 mark improvement for borderline students

- Higher confidence & exam temperament